## Sheet1
ANDROID CONTROLLED CAR
|  | START DATE | DURATION (days)
Learning Android Development |  | 2014-09-22 | 10
App Implementation |  | 2014-10-02 | 20
Signal communication |  | 2014-10-10 | 10
Hardware Implementation |  | 2014-10-20 | 20
Testing |  | 2014-11-10 | 12
Final Test |  | 2014-12-02 | 2
Completion |  | 2014-09-22 | 74

## Sheet2
| Start Date | Duration
Project Proposal | 2014-09-20 | 7
Software Requirements | 2014-09-27 | 7
Software Design Documents | 2014-10-04 | 7
System Prototype | 2014-10-08 | 31
Implementation | 2014-11-08 | 14
Software Test Plan | 2014-11-22 | 7
Project Deliverables | 2014-09-20 | 91